## Working Hours
Tasks | Hrs | Cost | cost/hour
Do Trainings | 110 | 3300 | 30
Make Node js Workshop | 40 | 1200 | 30
Take AngularJS crash course | 64 | 1920 | 30
Read Google Maps Integration Forms | 6 | 180 | 30
Secure HW | 96 | 1920 | 20
Secure Laptops | 40 | 800 | 20
Secure Servers | 16 | 320 | 20
Secure UPS | 40 | 800 | 524510
Install needed SW | 24 | 600 | 25
Install Visual studio code | 8 | 200 | 25
Install Node js | 8 | 200 | 25
Install angular | 8 | 200 | 25
Plan Processes | 120 | 6000 | 50
Plan Admin Story | 40 | 2000 | 50
Plan Moderators Story | 40 | 2000 | 50
Plan Clients Story | 40 | 2000 | 50
Setup Backend Server | 8 | 160 | 20
Install Apache | 2 | 40 | 20
Install Mysql | 2 | 40 | 20
Install Node js | 2 | 40 | 20
Install AngularJS | 2 | 40 | 20
Develop Mobile APP | 224 | 8960 | 40
Develop Request offer scenario | 80 | 3200 | 40
Develop See Offer Locations scenario | 40 | 1600 | 40
Develop Account Settings scenario | 48 | 1920 | 40
Develop Add/remove offers scenario | 56 | 2240 | 40
Total | 582 | 20940 | -----------
Total Price of working Hours + Tools and Services | ----------- | 524490 | -----------

## Tools and Services
Tools | Count | Price/1 | Total Price
Laptops | 8 | 10000 | 80000
UPS | 1 | 25000 | 25000
Services | Hrs | Price/hr | Total Price
AWS server | 26280 | 15 | 394200
Maintenance | 145 | 20 | 2900
Cleaning | 145 | 10 | 1450
Total Price | ----------- | ----------- | 503550
Total Price of working Hours + Tools and Services | ----------- | ----------- | 524490
503550

## Assumptions
The company is responsible for solving bugs for 3 years without extra credit
The company is responsible for putting the APP on google play and app store
The client is responsible for hiring a customer service (call center) company
The company is responsible for training the customer (call center) service company
The client is responsible for hiring moderators for the APP
The company is responsible for training the moderators for the APP
The client must pay for the AWS after 3 years
The client is responsible for paying for extra storage space on the server
The client is responsible making contacts with the offers providers (restaurants, ...)
The client is responsible for the marketing strategy