## Sheet1
Risk | Probability | Impact | Strategy | Action
Delay in development | Medium | High | Avoid | Training Development team at time of securing hardware
Security vulnerability in production | Low | High | Transfer | Hire a security expert to test app vulnerabilities before deploying production
Delay in getting google play certificate for the app | Medium | Low | Accept | No action