## Sheet1
Actual Project time (working days) | 10000 / (8*5) | 250
Actual Project time (Months) | 250/24 | 10.4167
Actual time after safety factor | 10.4 + 0.1* 10.4 | 12 Months
Earned value | 55% * 10000 | 5500
Assum time point now is 7 months
Is project overbudget? | yes | 7000-5500 = 1500
Is project delayed? | Planned Value = (7/12) * 10000 | 5833.3333
| yes | by 333 hours
delayed by how many days? | 333/(8*5) | 8.325
Plotting points
Time (months) | Actual Cost | Earned Value | Planned Value
1 | 1000 | 800 | 833.3333
2 | 1750 | 1620 | 1666.6667
3 | 2600 | 2200 | 2500
4 | 3800 | 3200 | 3333.3333
5 | 5000 | 3900 | 4166.6667
6 | 6100 | 4700 | 5000
7 | 7000 | 5500 | 5833.3333
8 | 8050 | 6268.5714 | 6666.6667
9 | 9089.2857 | 7052.8571 | 7500
10 | 10128.5714 | 7837.1429 | 8333.3333
11 | 11167.8571 | 8621.4286 | 9166.6667
12 | 12207.1429 | 10000 | 10000