## Sheet1
PBS
Discount card APP
Trainings | HW | SW | Process | Backend Server | Mobile APP
Node js | Laptops | Visual studio code | Admin | Apache | Request offer
AngularJS | Servers | Node js | Moderators | Mysql | See Offer Locations
Google Maps Integrations | UPS | angular | Clients | Node js | Account Settings
|  |  |  | AngularJS | Add/remove offers
WBS
Discount card APP
Do Trainings | Secure HW |  | Install needed SW | Plan Processes | Setup Backend Server | Develop Mobile APP
Make Node js Workshop | Secure Laptops | Select Laptops | Install Visual studio code | Plan Admin Story | Install Apache | Develop Request offer scenario | Make UI/UX
Take AngularJS crash course |  | Buy Laptops | Install Node js | Plan Moderators Story | Install Mysql |  | Develop
Read Google Maps Integration Forms |  | Setup Laptops | Install angular | Plan Clients Story | Install Node js |  | Test
| Secure Servers | Choose Provider |  |  | Install AngularJS |  | Deploy
|  | Setup Server |  |  |  | Develop See Offer Locations scenario | Make UI/UX
| Secure UPS | Choose supplier |  |  |  |  | Develop
|  | buy UPS |  |  |  |  | Test
|  | Setup UPS |  |  |  |  | Deploy
[6 empty] | Develop Account Settings scenario | Make UI/UX
Develop
Test
Deploy
[6 empty] | Develop Add/remove offers scenario | Make UI/UX
Develop
Test
Deploy
OBS
Discount card APP
Trainers | Supply Chain | Developers | Tester | DevOPs | UI/UX
| Manager | Team Lead | Team Lead | Team Lead | Team Lead
NodeJs workshop trainer | supply chain 1 | Mobile frontend developer 1 | Tester 1 | Devops 1 | UI/UX 1
AngularJs content creator | supply chain 2 | Mobile frontend developer 2 | Tester 2 |  | UI/UX 2
Backend Developer 1